## Sheet1
FOREST_NAME | WATERSHED_CODE | WATERSHED_NAME | WATERSHED_CONDITION_FS_AREA | TOTAL_WATERSHED_AREA_ACRES | FS_OWNERSHIP_PERCENT | NONFS_AREA_PERCENT | AQUATIC_BIOTA_CONDITION | RIPARIAN_WETLAND_VEG_CONDITION | WATER_QUALITY_CONDITION | WATER_QUANTITY_CONDITION | AQUATIC_HABITAT_CONDITION | ROADS_AND_TRAILS_CONDITION | SOIL_CONDITION | FIRE_EFFECTS_REGIME_CONDITION | FOREST_COVER_CONDITION | FOREST_HEALTH_CONDITION | INVASIVE_SPECIES_CONDITION | RANGELAND_VEGETATION_CONDITION | YEAR_PRIORITY_IDENTIFIED | PRINCIPAL_REASON | SELECTION_NARRATIVE | KNOWN_PARTNERS | APPROVAL_DATE | ESTIMATED_COMPLETION_DATE | ESSENTIAL_PROJECT_COUNT | ESSENTIAL_PROJECT_EST_COST | ACTUAL_COMPLETION_DATE | RESTORATION_ACTION_PLAN_IND | FS_UNIT_ID | WRAP_NAME | WRAP_APPROVAL_DATE | ACCOMPLISH_REPORT_IND | USFS_OWNERSHIP_ACRES | SHAPE_AREA | SHAPE_LEN
Grand Mesa Uncomp Gunnison National Forest | 140200010204 | Coal Creek | Functioning at Risk | 13146.4 | 78 | 22 | Poor | Fair | Poor | Good | Fair | Poor | Good | Good | Good | Fair | Good | Good | 2011 | <Principal_Reason><Resources><Resource><Value>Municipal Watershed</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Water Quantity</Value | Municiple Watershed for the town of Crested Butte. High Priority 303(d)listed stream segments for Cd, Zn, As, Mn, Pb, and Cu. Partnerships are in place. |  | 2018-04-09 | 2018-05-01 | 5 | 325695 | 2018-05-01 | Y | 0204 |  | 2018-04-09 | Y | 10262.86 | 0.0055216 | 0.35715
Kaibab National Forest | 150100040802 | Coconino Wash Headwaters | Functioning Properly | 51202.2 | 73 | 28 | Fair | Good | Fair | Fair | Good | Fair | Good | Good | Good | Good | Fair | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Wildfire Risk</Value></Concern><Concern><Value>Invasive Species</Value></Concern><Concern><Value>Riparian Structure and Function</Value></Concern></Concerns><Cost>$1 million to $5 million</Cost></Principal_Reaso | Forests are overstocked and have excessive fuel loading. There has been an increase in wildfires with moderate and high burn severity. The fires regime condition class is departed from its natural range of variability. The watershed has high road density | <Known_Partners><Partner><Name>AZ DOT</Name><Type>Known</Type></Partner><Partner><Name>AZ DOT Natural Resource Managment Sectio</Name><Type>Known</Type></Partner><Partner><Name>Alamo Navajo Indian Reservation</Name><Type>Known</Type></Partner><Partner><Na | 2011-12-04 | 2015-09-30 | 5 | 3123585 | 2015-09-10 | Y | 0307 | FY2011 Transition Watershed Restoration Action Plan-Kaibab National Forest | 2011-12-04 | Y | 37114.144 | 0.020711 | 0.8242
Gila National Forest | 150400010503 | Snow Canyon | Functioning at Risk | 31337.8 | 100 | 0 | Poor | Fair | Fair | Poor | Poor | Fair | Fair | Fair | Poor | Good | Good | Good | 2011 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Species Protection Area</Value></Resource><Resource><Value>Other</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></C | this is the only Impaired watershed on the Forest. It is right on the borderline of Impaired and Functional at Risk. With minimal investment and a few projects, it is expected that this watershed can move up a condition class into Functional At Risk wit | <Known_Partners><Partner><Name>New Mexico Environment Depart</Name><Type>Known</Type></Partner><Partner><Name>Catron County YCC</Name><Type>Known</Type></Partner><Partner><Name>Aldo Leopold YCC</Name><Type>Known</Type></Partner><Partner><Name>Wellness Coa | 2011-09-30 | 2016-12-31 | 4 | 845240 | 2016-09-29 | Y | 0306 | Snow Canyon Watershed Restoration Action Plan | 2011-09-30 | Y | 31331.185 | 0.012299 | 0.63087
Prescott National Forest | 150602020705 | Cherry Creek | Functioning at Risk | 15875 | 92 | 8 | Good | Good | Fair | Poor | Good | Poor | Fair | Fair | Good | Good | Good | Poor | 2011 | <Principal_Reason><Concerns><Concern><Value>Wildfire Risk</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Water Quantity</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | Primary concerns within the watershed are related to water resources and their influence on the Verde River system. Water quality issues within the watershed are sedimentation associated with inherently unstable granite parent material. Potential stress | <Known_Partners><Partner><Name>National Wild Turkey Federation</Name><Type>Known</Type></Partner><Partner><Name>Mule Deer Foundation</Name><Type>Known</Type></Partner></Known_Partners> | 2011-09-28 | 2016-09-30 | 21 | 773273 | 2015-09-30 | Y | 0309 | FY2011 TRANSITION WATERSHED RESTORATION ACTION PLAN, Verde District, Prescott National Forest, Cherry Creek, 150602020705 | 2011-09-28 | Y | 14614.512 | 0.0063516 | 0.57555
Grand Mesa Uncomp Gunnison National Forest | 140200030103 | Marshall Creek | Functioning at Risk | 36746.1 | 93 | 7 | Poor | Fair | Good | Fair | Poor | Fair | Good | Good | Good | Fair | Good | Good | 2011 | <Principal_Reason><Resources><Resource><Value>Outstanding Resource Water</Value></Resource><Resource><Value>Species Protection Area</Value></Resource></Resources><Cost>$100,000 to $1 million</Cost></Principal_Reason> | The Marshall Creek watershed is a high priority for restoration on the GMUG because of our existing partnerships that are in place and well funded. | <Known_Partners><Partner><Name>Saguache County RAC</Name><Type>Known</Type></Partner></Known_Partners> | 2011-09-30 | 2016-10-01 | 6 | 464881 | 2013-09-30 | Y | 0204 | Marshall Creek, Saguache County, Colorado | 2011-09-30 | Y | 34288.335 | 0.015328 | 0.63136
Idaho Panhandle National Forest | 170102131204 | Lower Lightning Creek | Functioning at Risk | 20522.8 | 72 | 28 | Fair | Fair | Poor | Good | Fair | Good | Good | Good | Good | Good | Fair | Fair | 2014 | <Principal_Reason><Concerns><Concern><Value>Other</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Riparian Structure and Function</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | High road density, roads in floodplains, reduced aquatic and riparian habitat complexity, elevated stream temps. | <Known_Partners><Partner><Name>Avista</Name><Type>Known</Type></Partner><Partner><Name>National Forest Foundation</Name><Type>Known</Type></Partner><Partner><Name>Friends of Scotchman Peaks Wilderness</Name><Type>Known</Type></Partner><Partner><Name>Trout | 2013-12-17 | 2016-09-30 | 2 | 210000 | 2015-10-31 | Y | 0104 | Lower and Middle Lightning Creek WRAP | 2013-12-17 | Y | 14790.492 | 0.010048 | 0.55932
Klamath National Forest | 180102080601 | Canyon Creek | Functioning Properly | 15835.7 | 98 | 2 | Good | Good | Fair | Good | Good | Good | Good | Fair | Good | Fair | Fair | Good | 2012 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Wild and Scenic River</Value></Resource><Resource><Value>Other</Value></Resource></Resources><Concerns><Concern><Value>Water Quality</Value></Concern><Concern><Val | This watershed has a long history of restoration work that predates the WCF. In 2012 the last remaining projects were completed under the WCF. A formal WRAP has not been completed. | [5 empty] | 2012-09-30 |  | 0505 |  |  |  | 15581.971 | 0.0069187 | 0.37271
Mt Baker-Snoqualmie National Forest | 171100060304 | Big Creek | Functioning Properly | 13831.1 | 98 | 2 | Good | Good | Good | Good | Good | Good | Good | Good | Good | Good | Good | ---- | 2016 | <Principal_Reason><Resources><Resource><Value>Wild and Scenic River</Value></Resource><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Water Quality</Value></Concern><Concern><Value>Species Habitat</Value></ | The Sauk River is the largest free-flowing tributary of the Skagit Wild & Scenic River, and supports spawning runs of all five Pacific salmon species. Big Creek is one of four index tributaries of the Suiattle River (a major trib of the Sauk and a NWFP k | <Known_Partners><Partner><Name>Skagit River System Cooperative</Name><Type>Known</Type></Partner><Partner><Name>Skagit Watershed Council</Name><Type>Known</Type></Partner></Known_Partners> | 2016-10-04 | 2017-10-15 | 2 | 318264 | 2017-09-29 | Y | 0605 | Big Creek WRAP | 2016-10-04 | Y | 13601.942 | 0.0067569 | 0.46592
Deschutes National Forest | 170703010702 | Upper Whychus Creek | Functioning at Risk | 18293.8 | 93 | 7 | Poor | Fair | Poor | Fair | Good | Fair | Good | Fair | Poor | Good | Good | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Wild and Scenic River</Value></Resource><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species | Many projects are being planned/implemented and many partners are already working for restoration of fish passage/fish screens, flow protection, floodplain protection and habitat restoration and aquatic education. Chinook salmon and steelhead trout are b | <Known_Partners><Partner><Name>Upper Deschutes Watershed Council</Name><Type>Known</Type></Partner><Partner><Name>Trout Unlimited</Name><Type>Known</Type></Partner><Partner><Name>Portland General Electric</Name><Type>Known</Type></Partner><Partner><Name>O | 2011-09-09 | 2017-09-09 | 9 | 1279500 | 2017-07-28 | Y | 0601 | Upper Whychus Creek | 2011-09-09 | Y | 17038.41 | 0.0083426 | 0.70221
Bridger-Teton National Forest | 170401030107 | Fall Creek | Functioning Properly | 30025.1 | 98 | 2 | Good | Fair | Good | Good | Good | Poor | Fair | Fair | Good | Good | Poor | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Invasive Species</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | Opportunities to improve riparian conditions and recreational uses to be compatible with protecting water quality. |  | 2011-09-30 | 2017-09-30 |  |  | 2017-10-15 | Y | 0403 | Fall Creek Action Plan | 2011-09-30 |  | 29320.887 | 0.013489 | 0.64922
Nez Perce Clearwater National Forest | 170603050702 | Meadow Creek | Functioning Properly | 24022.6 | 99 | 1 | Good | Good | Poor | Good | Fair | Good | Fair | Fair | Good | Good | Good | Good | 2014 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | Degraded meadow condition contribuing to high stream temps. Timber harvest, grazing and road building led to excessive sediment in Meadow Creek. High road density. | <Known_Partners><Partner><Name>Nez Perce Tribe</Name><Type>Known</Type></Partner></Known_Partners> | 2014-06-29 | 2018-09-30 | 5 | 223500 | 2015-09-01 | Y | 0117 | Meadow Creek WRAP | 2014-06-29 | Y | 23837.112 | 0.011273 | 0.57073
Umatilla National Forest | 170701020301 | Upper North Fork Touchet River | Functioning Properly | 17774.6 | 88 | 13 | Good | Fair | Good | Good | Fair | Fair | Good | Good | Good | Fair | Good | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Socio-Economic Benef | The subwatershed is a focus for ongoing investments, partnerships, and is a TRACS habitat conservation and restoration priority | <Known_Partners><Partner><Name>Washington Department of Fish and Wildli</Name><Type>Known</Type></Partner><Partner><Name>Tri State Steelheaders</Name><Type>Known</Type></Partner><Partner><Name>Confederated Tribes of the Umatilla Indi</Name><Type>Known</Ty | 2012-09-19 | 2016-09-30 | 6 | 320000 | 2016-09-30 | Y | 0614 | 2012 Upper North Fork Touchet River Watershed Restoration Action Plan - Updated in 2016 | 2012-09-19 | Y | 15549.807 | 0.0083892 | 0.5081
Wallowa Whitman National Forest | 170601040206 | Lower Meadow Creek | Functioning at Risk | 27171.1 | 67 | 33 | Fair | Fair | Good | Good | Fair | Poor | Good | Poor | Good | Good | Good | Fair | 2013 | <Principal_Reason><Resources><Resource><Value>Species Protection Area</Value></Resource></Resources><Cost>$100,000 to $1 million</Cost></Principal_Reason> | Provide habitat for ESA listed fish species: Bull Trout, Summer Steelhead, and Spring Chinook | <Known_Partners><Partner><Name>Bonneville Power Association</Name><Type>Known</Type></Partner><Partner><Name>Grande Ronde Model Watershed Council</Name><Type>Known</Type></Partner><Partner><Name>Confederated Tribes of the Umatilla</Name><Type>Known</Type> | 2013-02-28 | 2013-09-30 | 1 | 300000 | 2013-09-30 | Y | 0616 | Meadow Creek TWRAP Update 2/28/2013 | 2013-02-28 | Y | 18140.598 | 0.012594 | 0.6424
Siuslaw National Forest | 171002050303 | Lower Drift Creek | Functioning Properly | 19139.4 | 91 | 10 | Good | Good | Fair | Good | Fair | Poor | Good | Fair | Good | Good | Good | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Opportunity><Opportunity><Value>L | Lower Drift Creek was included in the Alsea River focus watershed before the watershed boundaries were redrawn to exclude it. The Forest and its partners have been working in Drift Creek and the Alsea River for years and are getting close to completing a | <Known_Partners><Partner><Name>Lincoln County</Name><Type>Known</Type></Partner><Partner><Name>Alsea Watershed Council</Name><Type>Known</Type></Partner><Partner><Name>Mid Coast Watershed Council</Name><Type>Known</Type></Partner></Known_Partners> | 2012-10-04 | 2016-09-30 | 6 | 127000 | 2016-09-15 | Y | 0612 | LOWER DRIFT CREEK (ALSEA RIVER) WATERSHED RESTORATION ACTION PLAN | 2012-10-04 | Y | 17329.255 | 0.0087376 | 0.52105
Siuslaw National Forest | 171002060701 | Upper North Fork Siuslaw River | Functioning Properly | 22763.3 | 88 | 12 | Good | Fair | Fair | Good | Good | Fair | Good | Fair | Good | Good | Good | ---- | 2011 | <Principal_Reason><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Potential Partnership</Value></Opportunity></Opportunities><Cost>$1 million to $5 million</Cost></Principal_Reason> | The Upper North Fork Siuslaw River 6th field is contained within the special emphasis North Fork Siuslaw River 5th field area, located on the Siuslaw National Forest. The Upper North Fork Siuslaw River 6th field contains a high percentage of National Fore | <Known_Partners><Partner><Name>Siuslaw Institute</Name><Type>Known</Type></Partner><Partner><Name>Florence Salmon-Trout Enhancement Progra</Name><Type>Known</Type></Partner><Partner><Name>Siuslaw School District</Name><Type>Known</Type></Partner><Partner> | 2011-09-30 | 2015-09-30 | 11 | 2676000 | 2015-07-31 | Y | 0612 | FY2011 TRANSITION WATERSHED RESTORATION ACTION PLAN for UPPER NORTH FORK SIUSLAW RIVER | 2011-09-30 | Y | 20089.817 | 0.010358 | 0.4819
Tongass National Forest | 190102110501 | 190102110501 | Functioning Properly | 17939.6 | 98 | 2 | Good | Poor | Good | Good | Fair | Good | Good | Good | Good | Good | Good | ---- | 2011 |  | There is concern for the long term health and function of aquatic and riparian habitat in the Sitkoh River Watershed. A significant percentage of riparian area associated with wood-dependent streams has been harvested or roaded. Indicators for Instream | <Known_Partners><Partner><Name>Sitka Conservation Society</Name><Type>Known</Type></Partner><Partner><Name>Alaska Sustainable Salmon Fund</Name><Type>Known</Type></Partner><Partner><Name>Trout Unlimited</Name><Type>Known</Type></Partner></Known_Partners> | 2011-01-01 | 2013-01-01 | 3 | 900000 | 2014-09-30 | Y | 1005 | Sitkoh River/Bay Restoration | 2011-01-01 | Y | 17651.753 | 0.010912 | 0.63352
Daniel Boone National Forest | 051002040206 | Gladie Creek-Red River | Functioning Properly | 20892.1 | 52 | 48 | Fair | Good | Good | Good | Fair | Fair | Fair | Fair | Good | Good | Good | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Outstanding Resource Water</Value></Resource><Resource><Value>Wild and Scenic River</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and | This watershed was chosen because it is one of the four watersheds where we have multiple issues that are being addressed by a collaborative Watershed Protection Plan. | <Known_Partners><Partner><Name>Kentucky Division of Water</Name><Type>Known</Type></Partner><Partner><Name>Kentucky Department of Fish and Wildlife</Name><Type>Known</Type></Partner><Partner><Name>Kentucky Waterways Alliance</Name><Type>Known</Type></Part | 2011-09-30 | 2016-12-31 | 3 | 50000 | 2013-09-30 | Y | 0802 | Red River Gorge Watershed Protection Plan | 2011-09-30 | Y | 10770.992 | 0.0086529 | 0.77074
Cherokee National Forest | 060101080608 | Nolichucky River-Clark Creek | Functioning at Risk | 43046.1 | 50 | 50 | Fair | Fair | Fair | Good | Good | Poor | Poor | Poor | Fair | Fair | Poor | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Other</Value></Resource><Resource><Value>Species Protection Area</Value></Resource><Resource><Value>Municipal Watershed</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</ | The overall objective of the restoration project is to improve the condition of the watershed by decreasing erosion/sedimentation and improving riparian conditions, water quality and stream channel conditions, control invasive non-native species, and rest | <Known_Partners><Partner><Name>USFWS Fish Passage Program</Name><Type>Known</Type></Partner><Partner><Name>TDEC</Name><Type>Known</Type></Partner><Partner><Name>TVA</Name><Type>Known</Type></Partner><Partner><Name>Tennessee Wildlife Resources Agency</Name | 2011-10-17 | 2016-12-31 | 6 | 139000 | 2017-08-01 | Y | 0804 | FY2011 TRANSITION WATERSHED RESTORATION ACTION PLAN | 2011-10-17 | Y | 21451.221 | 0.017449 | 0.87039
Lewis And Clark National Forest | 100301050104 | Lower Dry Fork Belt Creek | Functioning at Risk | 21291 | 88 | 12 | Poor | Fair | Poor | Fair | Poor | Fair | Fair | Fair | Good | Fair | Poor | Good | 2014 | <Principal_Reason><Concerns><Concern><Value>Water Quantity</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | 303d for heavy metals. Contaminated sediment delivery and acid mine drainage to streams. High forest road densities close to streams. Invasive weeds. Mountain pine beetle effecting hydrologic function. Pure populations of west slope cutthroat traout. Very | <Known_Partners><Partner><Name>Montana Fish, Wildlife and Parks</Name><Type>Known</Type></Partner><Partner><Name>US Environmental Protrection Agency</Name><Type>Known</Type></Partner></Known_Partners> | 2014-06-30 | 2017-09-30 | 3 | 300000 | 2017-09-01 | Y | 0115 | Lower Dry Fork Belt creek | 2014-06-30 | Y | 18751.642 | 0.010205 | 0.51791
Kisatchie National Forest | 111402070204 | Steep Hill Creek-Kisatchie Bayou | Functioning Properly | 24082.8 | 87 | 13 | Good | Good | Good | Good | Fair | Good | Fair | Poor | Fair | Good | Poor | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Other</Value></Resource><Resource><Value>Wild and Scenic River</Value></Resource></Resources><Concerns><Concern><Value>Wildfire Risk</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Va | The Watershed Condition Classification process indicated that Steep Hill Creek-Kisatchie Bayou watershed was in need of maintenance activities to keep it functioning properly. This watershed is one of high watershed resource value as it contains a State | <Known_Partners><Partner><Name>Natchitoches Parish Correctional Facilit</Name><Type>Known</Type></Partner><Partner><Name>Louisiana Department of Environmental Qu</Name><Type>Known</Type></Partner></Known_Partners> | 2011-10-21 | 2016-09-30 | 6 | 5920380 | 2018-03-13 | Y | 0806 | Steep Hill Creek-Kisatchie Bayou | 2011-10-21 |  | 20962.953 | 0.0092532 | 0.55185
Kaibab National Forest | 150100040201 | Upper Spring Valley Wash | Functioning at Risk | 38282 | 92 | 8 | Fair | Poor | Fair | Fair | Poor | Fair | Fair | Fair | Fair | Fair | Poor | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Wildfire Risk</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Invasive Species</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Opp | Forests are currently overstocked and have excessive fuel loading. There has been an increase in wildfires with moderate/high burn severity (2011 Beale Fire, 2010 Eagle Rock Fire, 2009 Marteen Fire, and 2000 Pumpkin Fire). Unstable volcanic soils have und | <Known_Partners><Partner><Name>Roads construction and maintenance contr</Name><Type>Known</Type></Partner><Partner><Name>Logging and TSI contractors</Name><Type>Known</Type></Partner><Partner><Name>Noxious Weeds Mitigation Contractors</Name><Type>Known</T | 2011-09-12 | 2016-12-31 | 7 | 3752000 | 2014-09-25 | Y | 0307 | Upper Spring Valley Wash Transition Watershed Restoration Action Plan | 2011-09-12 | Y | 35125.701 | 0.015387 | 0.71063
Prescott National Forest | 150701020102 | Upper Ash Creek | Functioning at Risk | 27313.8 | 97 | 3 | Good | Fair | Fair | Fair | Good | Poor | Fair | Fair | Good | Good | Good | Fair | 2013 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Water Quantity</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | Primary concerns within the watershed are related to soil and water resources and their influence on the Agua Fria River system. Water quantity issues include maintenance of numerous springs, and associated riparian corridors throughout the Ash Creek drai | <Known_Partners><Partner><Name>Prescott Yavapai County Youth Conservati</Name><Type>Known</Type></Partner><Partner><Name>Verde Watershed Restoration Coalition</Name><Type>Known</Type></Partner><Partner><Name>Arizona Game and Fish Department</Name><Type>Kn | 2013-09-30 | 2017-09-30 | 29 | 805600 | 2017-09-30 | Y | 0309 | Upper Ash Creek Watershed Restoration Action Plan, Verde Ranger District, Prescott National Forest | 2013-09-30 |  | 26577.407 | 0.010865 | 0.65348
Bitterroot National Forest | 170102050405 | East Fork Bitterroot River-Bartie Lord Creek | Functioning at Risk | 10985.2 | 94 | 6 | Fair | Fair | Fair | Good | Fair | Fair | Fair | Fair | Good | Fair | Fair | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restora | The Bertie Lord watershed is located within the Martin Creek project area on the Sula Ranger District. The Martin Creek project involves decommissioning of non-system, historical roads that are not needed for future management. The project analyzed a tota | <Known_Partners><Partner><Name>Trout Unlimited</Name><Type>Known</Type></Partner><Partner><Name>Clark Fork Coalition</Name><Type>Known</Type></Partner><Partner><Name>Bitterroot Water Forum</Name><Type>Known</Type></Partner></Known_Partners> | 2011-11-10 | 2013-09-30 | 1 | 162000 | 2013-09-30 | Y | 0103 | Bertie Lord Watershed Restoration Action Plan | 2011-11-10 | Y | 10350.643 | 0.0051563 | 0.39469
Olympic National Forest | 171100170101 | Upper South Fork Skokomish River | Functioning at Risk | 38707.9 | 95 | 5 | Fair | Good | Fair | Good | Fair | Fair | Fair | Good | Good | Good | Good | ---- | 2007 | <Principal_Reason><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Opportunity><Opportunity><Value>Potential Partnership</Value></Opportunity><Opportunity><Value>Improve Condition</Value></Opportunity></Opportunities><Cost>$1 million t | One of the Forest's best opportunities to recovery listed bull trout, and link in with a highly functioning and effect collaborative restoration group, Skokomish Watershed Action Team; extensive restoration opportunities in the subwatershed. | <Known_Partners><Partner><Name>Skokomish Watershed Action Team</Name><Type>Known</Type></Partner><Partner><Name>Skokomish Tribe</Name><Type>Known</Type></Partner></Known_Partners> | 2012-09-28 | 2016-09-30 | 6 | 3862000 | 2015-12-31 | Y | 0609 | Upper South Fork Skokomish River Watershed Restoration Action Plan | 2012-09-28 | Y | 36922.361 | 0.018602 | 0.84434
Mt Baker-Snoqualmie National Forest | 171100060203 | Sulphur Creek | Functioning Properly | 20897.3 | 100 | 0 | Good | Good | Good | Good | Good | Good | Good | Good | Good | Good | Good | ---- | 2015 | <Principal_Reason><Resources><Resource><Value>Wild and Scenic River</Value></Resource></Resources><Concerns><Concern><Value>Water Quality</Value></Concern><Concern><Value>Species Habitat</Value></Concern></Concerns></Principal_Reason> | Selected for priority watershed because of Skagit Wild and Scenic River values and salmon, steelhead and bull trout recovery needs. | <Known_Partners><Partner><Name>WA Department of Fish &amp; Wildlife</Name><Type>Known</Type></Partner><Partner><Name>Federal Highways Administration</Name><Type>Known</Type></Partner><Partner><Name>Seattle City Light</Name><Type>Known</Type></Partner><Par | 2015-09-20 | 2017-10-01 | 3 | 1726000 | 2016-09-30 | Y | 0605 | Sulphur Creek Watershed Watershed Restoration Action Plan | 2015-09-20 | Y | 20897.25 | 0.010393 | 0.55503
Siuslaw National Forest | 171002030209 | Farmer Creek-Nestucca River | Functioning Properly | 18089.3 | 55 | 45 | Fair | Fair | Good | Good | Fair | Fair | Good | Fair | Good | Good | Good | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</V | Farmer Creek is a high value subwatershed within the Nestucca River Focus Watershed. The Forest and its partners have been working in the Nestucca River watershed for years completing essential projects. While we have completed many essential projects o | <Known_Partners><Partner><Name>Oregon Watershed Enhancement Board</Name><Type>Known</Type></Partner><Partner><Name>Tillamook Estuaries Partnership</Name><Type>Known</Type></Partner><Partner><Name>Forest Service Payments to Counties</Name><Type>Known</Type | 2012-10-01 | 2015-09-30 | 7 | 1636392 | 2015-09-15 | Y | 0612 | Farmer Creek Watershed Restoration Action Plan | 2012-10-01 | Y | 9934.473 | 0.008396 | 0.5598
Wallowa Whitman National Forest | 170601040202 | Middle Meadow Creek | Functioning at Risk | 22269 | 96 | 4 | Fair | Fair | Good | Good | Fair | Poor | Good | Poor | Good | Good | Good | Fair | 2012 | <Principal_Reason><Resources><Resource><Value>Species Protection Area</Value></Resource></Resources><Cost>$100,000 to $1 million</Cost></Principal_Reason> | This subwatershed is an important component of the upper Grande Ronde River system, which provides critical spawning and rearing habitat for wild stocks of listed Snake River Steelhead and Spring Chinook Salmon. Restoration efforts will enhance recovery e | <Known_Partners><Partner><Name>Grande Ronde Model Watershed</Name><Type>Known</Type></Partner><Partner><Name>Confederated Tribes Umatilla Indian Rese</Name><Type>Known</Type></Partner><Partner><Name>Bonneville Power Administration</Name><Type>Known</Type> | 2012-02-28 | 2013-09-30 | 1 | 500000 | 2013-09-30 | Y | 0616 | Meadow Creek TWRAP Update 2/28/2013 | 2012-02-28 | Y | 21404.603 | 0.010329 | 0.51034
Land Between The Lakes Nra | 051302050408 | Dry Creek-Cumberland River | Functioning Properly | 49241.4 | 46 | 54 | Good | Good | Good | Fair | Good | Fair | Fair | Fair | Good | Good | Fair | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Invasive Species</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Potential Partnership</Va | Failed culverts and associated sedimentation of road ditches. Cultivated fields. | <Known_Partners><Partner><Name>USDA NRCS</Name><Type>Known</Type></Partner><Partner><Name>Permitee Farmers</Name><Type>Known</Type></Partner><Partner><Name>Trigg County Conservation District</Name><Type>Known</Type></Partner></Known_Partners> | 2011-10-28 | 2014-12-31 | 5 | 578967 | 2015-09-25 | Y | 0860 | Dry Creek-Cumberland River Watershed Restoration Action Plan | 2011-10-28 | Y | 22701.869 | 0.020092 | 0.91173
Dakota Prairie Grasslands | 090202040504 | Pigeon Point-Sheyenne River | Functioning Properly | 51739.9 | 19 | 81 | Fair | Good | Good | Good | Good | Fair | Good | Fair | ---- | Fair | Fair | Fair | 2014 | <Principal_Reason><Concerns><Concern><Value>Invasive Species</Value></Concern><Concern><Value>Species Habitat</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | This watershed is characterized by a shallow water table with groundwater dependent ecosystems present throughout. Small wetlands and groundwater fed springs, seeps, fens and wet meadow ecosystems are common and serve as recharge areas for the Sheyenne D | <Known_Partners><Partner><Name>Sheyenne Valley Grazing Association</Name><Type>Known</Type></Partner></Known_Partners> | 2014-10-01 | 2017-09-30 | 4 | 175000 | 2017-02-08 | Y | 0118 | FY15 Watershed Restoration Action Plan, Sheyenne Ranger District, Pigeon Point - Sheyenne River. | 2014-10-01 | Y | 9689.399 | 0.024536 | 1.0044
Bighorn National Forest | 100901010103 | Upper South Tongue River | Functioning at Risk | 31048.7 | 100 | 0 | Poor | Poor | Good | Good | Poor | Fair | Fair | Fair | Good | Good | Good | Good | 2011 | <Principal_Reason><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Leverage Forest Service Funds</Value></Opportunity><Opportunity><Value>Potential Partnership</Value></Opportunity></Opportunities><Cost>$100,00 | The Upper Tongue River watershed was previously identified in the Aquatics, Riparian and Wetland Ecosystem Assessment (Winters, 2004) as one most in need of improvement. Several watershed improvement projects have been completed in this watershed and des | <Known_Partners><Partner><Name>Trout Unlimited</Name><Type>Known</Type></Partner><Partner><Name>Rocky Mountain Elk Foundation</Name><Type>Known</Type></Partner><Partner><Name>Grazing permittee</Name><Type>Known</Type></Partner><Partner><Name>Wyoming Wildl | 2011-10-01 | 2018-10-01 | 7 | 600000 | 2017-09-29 | Y | 0202 | FY2011 TRANSITION WATERSHED RESTORATION ACTION PLAN, Upper Tongue River, Bighorn National Forest | 2011-10-01 | Y | 31048.642 | 0.014257 | 0.66571
Dakota Prairie Grasslands | 101303010504 | Deer Creek-North Fork Grand River | Functioning at Risk | 22498.4 | 34 | 66 | Fair | Good | Poor | Poor | Fair | Poor | Good | Fair | ---- | Fair | Fair | Good | 2014 | <Principal_Reason><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Potential Partnership</Value></Opportunity></Opportunities><Cost>&lt; $100,000</Cost></Principal_Reason> | Selected because of the opportunity to improve range vegetation, riparian, and stream habitat conditions along Deer Creek and Billy Young Creek in the Grand River National Grasslands. |  | 2013-01-22 | 2014-09-30 | 5 | 100000 | 2014-09-30 | Y | 0118 | Watershed Restoration Action Plan for Deer Creek - North Fork Grand River, Grand River Ranger District. | 2013-01-22 | Y | 7649.313 | 0.01055 | 0.62425
Pike-San Isabel National Forest | 110200101801 | Minnie Canyon-Purgatorie River | Functioning Properly | 24842.9 | 35 | 65 | Fair | Good | Fair | Good | Fair | Good | Good | Good | ---- | Good | Good | Fair | 2011 | <Principal_Reason><Resources><Resource><Value>Other</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Invasive Species</Value></Concern></Concerns></Principal_Reason> | Protection and improvement of existing watershed condition through invasive species treatement, and road and trail improvements |  |  | 2014-12-31 |  | 100000 | 2015-08-01 | Y | 0212 | Minnie-Canyon Purgatoire River - 110200101801 |  | Y | 8656.718 | 0.010258 | 0.61331
Gifford Pinchot National Forest | 170800020204 | Lower Clear Creek | Functioning at Risk | 12297.4 | 100 | 0 | Poor | Good | Fair | Good | Poor | Fair | Good | Fair | Good | Good | Good | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Invasive Species</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Rest | The Gifford Pinchot NF Aquatic Health Assessment prioritized watersheds for restoration in 2002. The assessment was conducted at the watershed scale and based on data from forest lands. The three primary criteria for analysis were resource condition, in | <Known_Partners><Partner><Name>Lower Columbia Fish Recovery Board</Name><Type>Known</Type></Partner><Partner><Name>Lewis River Collaborative Group</Name><Type>Known</Type></Partner><Partner><Name>Cowlitz Indian Tribe</Name><Type>Known</Type></Partner><Par | 2010-10-01 |  | 17 | 425000 | 2014-09-30 | Y | 0603 | Gifford Pinchot NF Action Plan-Lower Muddy, Lower Clear and Slide Creek-East Fork Lewis - Signature page attached to Lower Muddy River Subwatershed. | 2010-10-01 | Y | 12297.403 | 0.0057873 | 0.40182
Sawtooth National Forest | 170602010204 | Pole Creek | Functioning at Risk | 13021.5 | 94 | 6 | Poor | Fair | Good | Good | Poor | Poor | Good | Fair | Good | Good | Good | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Wildfire Risk</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity | Aquatic habitat is functioning at risk in localized areas due to sedimentation and other impacts from roads, developed and dispersed recreation, livestock grazing, and past mining. Native fish and amphibian populations are at risk due to the presence of | <Known_Partners><Partner><Name>Salmon Falls Land and Livestock</Name><Type>Known</Type></Partner><Partner><Name>Idaho Department of Water Resources</Name><Type>Known</Type></Partner><Partner><Name>Natural Resources Conservation Service</Name><Type>Known</ | 2011-09-30 | 2017-09-30 | 9 | 14170000 | 2017-08-31 | Y | 0414 | Pole Creek Watershed Action Plan | 2011-09-30 | Y | 12205.41 | 0.0059066 | 0.46389
Bridger-Teton National Forest | 170401030304 | Muddy Creek | Functioning Properly | 18786 | 77 | 23 | Good | Fair | Good | Good | Fair | Poor | Fair | Fair | Good | Good | Good | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Socio-Econ | Of immediate concern are locations where ATV’s have explored multiple stream crossings and locations where open roads contribute sediment to streams and wet areas. Important ecological values: key wildlife habitat for moose elk deer and grizzly bears. | <Known_Partners><Partner><Name>grazing permitees</Name><Type>Known</Type></Partner></Known_Partners> | 2011-09-30 | 2015-09-30 | 2 | 105000 | 2015-09-30 | Y | 0403 | Muddy creek Hoback river | 2011-09-30 | Y | 14517.625 | 0.0084048 | 0.50946
Boise National Forest | 170602080402 | Curtis Creek | Functioning at Risk | 17486.2 | 100 | 0 | Fair | Fair | Good | Good | Poor | Poor | Good | Fair | Fair | Good | Fair | ---- | 2008 | <Principal_Reason><Resources><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Species Habitat</Value></Concern></Concerns></Principal_Reason> | This was the only sub-watershed not affected by the 2007 Cascade fire. It provided refugia for TES chinook, steelhead and bull trout. |  | 2009-06-03 | 2011-09-30 | 6 | 50000 | 2011-09-30 |  | 0402 | Curtis Creek AOP and road drainage improvement (CE) | 2009-06-03 |  | 17486.197 | 0.0080221 | 0.42627
Nez Perce Clearwater National Forest | 170603030303 | Fishing Creek | Functioning Properly | 17202 | 100 | 0 | Good | Fair | Good | Good | Good | Fair | Good | Good | Good | Good | Fair | Poor | 2011 | <Principal_Reason><Concerns><Concern><Value>Invasive Species</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></O | Fishing Creek has been a restoration priority for the Forest for over 15 years in partnership with the Nez Perce Tribe. The watershed is a stronghold for listed fish species, and has a legacy of effects from past management and insect infestations. | <Known_Partners><Partner><Name>Nez Perce Tribe</Name><Type>Known</Type></Partner><Partner><Name>Clearwater Basin Collaborative</Name><Type>Known</Type></Partner></Known_Partners> | 2011-10-28 | 2014-12-31 | 4 | 777000 | 2012-09-10 | Y | 0117 | Fishing Creek WRAP | 2011-10-28 | Y | 17202.031 | 0.0081678 | 0.47086
Mendocino National Forest | 180101040401 | Bear Creek-Elk Creek | Functioning Properly | 27875.2 | 67 | 33 | Good | Good | Fair | Good | Good | Good | Good | Fair | Good | Good | Good | Good | 2011 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Water Quality</Value></Concern></Concerns></Principal_Reason> | Watershed contains designated critical habitat for salmon and steelhead (ESA listed) and FS portion of the watershed is primarily in Yuki Wildnerness. Unauthorized motorized use is causing erosion and sedimentation. | <Known_Partners><Partner><Name>California State Parks OHV division</Name><Type>Known</Type></Partner></Known_Partners> | 2011-01-01 | 2012-09-30 | 3 | 95000 | 2012-09-30 |  | 0508 | Bear Creek- Elk Creek | 2011-01-01 | Y | 18662.549 | 0.011817 | 0.54049
Cherokee National Forest | 060101030306 | Watauga Lake | Functioning at Risk | 27198.3 | 49 | 51 | Poor | Fair | Good | Poor | Poor | Fair | Fair | Poor | Good | Fair | Fair | ---- | 2015 | <Principal_Reason><Resources><Resource><Value>Municipal Watershed</Value></Resource><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Qua | Domestic and agricultural water supply, several at-risk terrestrial species, coldwater and warmwater fish communities, potential brook trout habitat, habitat for demand wildlife species, and lake habitat and shoreline. Sediment entering stream from FS ro | <Known_Partners><Partner><Name>Local Volunteers</Name><Type>Known</Type></Partner><Partner><Name>Tennessee Wilslife Resources Agency</Name><Type>Known</Type></Partner></Known_Partners> | 2015-01-26 | 2018-09-30 | 14 | 304000 | 2017-08-01 | Y | 0804 | WATERSHED RESTORATION ACTION PLAN - WATAUGA LAKE | 2015-01-26 | Y | 13243.104 | 0.011048 | 0.5962
Monongahela National Forest | 050500030102 | Headwaters East Fork Greenbrier River | Functioning at Risk | 25259.5 | 84 | 17 | Fair | Fair | Good | Good | Poor | Fair | Poor | Good | Good | Good | Fair | Good | 2011 | <Principal_Reason><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Opportunity><Opportunity><Value>Other</Value></Opportunity><Opportunity><Value>Improve Condition</Value></Opportunity></Opportunities><Cost>$1 million to $5 million</Co | Results from the 2001 Watershed Integrity Ranking process and the 2010 Watershed Condition Classification process indicated the relative importance of this sub-watershed with respect to its condition, vulnerability, ecological importance, and the potentia | <Known_Partners><Partner><Name>Trout Unlimited</Name><Type>Known</Type></Partner><Partner><Name>Canan Valley Institute</Name><Type>Known</Type></Partner></Known_Partners> | 2011-10-28 | 2017-09-30 | 5 | 1765100 | 2016-09-30 | Y | 0921 | Headwaters East Fork Greenbrier River | 2011-10-28 | Y | 21094.527 | 0.010575 | 0.53209
Ouachita National Forest | 080401010402 | Middle South Fork Ouachita River | Functioning at Risk | 28165.1 | 61 | 40 | Good | Fair | Fair | Good | Fair | Poor | Good | Poor | Good | Good | Fair | ---- | 2015 | <Principal_Reason><Resources><Resource><Value>Municipal Watershed</Value></Resource><Resource><Value>Species Protection Area</Value></Resource><Resource><Value>Outstanding Resource Water</Value></Resource></Resources><Cost>&lt; $100,000</Cost></Principal_ | 1. To reduce the amount of soil erosion and sedimentation which is negatively affecting water quality and quantity and the natural hydrology of tributaries. 2. To improve water quality and quantity for the future for both municipal use and for the benefit | <Known_Partners><Partner><Name>Montgomery County</Name><Type>Known</Type></Partner><Partner><Name>Arkansas Game &amp; Fish Commission</Name><Type>Known</Type></Partner><Partner><Name>Arkansas State University</Name><Type>Known</Type></Partner></Known_Part | 2015-04-27 | 2020-09-30 | 3 | 462069 | 2018-01-01 | Y | 0809 | Middle South Fork Ouachita River | 2015-04-27 |  | 17037.703 | 0.011194 | 0.54123
Chippewa National Forest | 070101010508 | Cass Lake | Functioning at Risk | 36078.4 | 26 | 74 | Fair | Fair | Fair | Fair | Poor | Poor | Fair | Poor | Good | Good | Fair | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quantity</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</ | The Cass Lake Watershed is located within 90 river miles of the Headwaters of the Mississippi River. The watershed is rated as condition class II. This rating is primarily due to impacts related to Knutson Dam, which is located on the Mississippi River | <Known_Partners><Partner><Name>Midwest Glacial Lakes Partnership</Name><Type>Known</Type></Partner><Partner><Name>Otter Tail Power Company</Name><Type>Known</Type></Partner><Partner><Name>Leech Lake Band of Ojibwe</Name><Type>Known</Type></Partner><Partne | 2011-10-26 | 2020-09-30 | 4 | 1450000 | 2016-09-20 | Y | 0903 | Cass Lake WRAP | 2011-10-26 | Y | 9293.194 | 0.017418 | 0.84393
Custer Gallatin National Forest | 100200081202 | Pass Creek | Functioning Properly | 13172.7 | 46 | 54 | Poor | Good | Good | Good | Poor | Fair | Good | Fair | Good | Good | Good | Good | 2012 | <Principal_Reason><Concerns><Concern><Value>Invasive Species</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</Value></Opportun | Excessive roads and road conditions resulted in sediment issues prior to rehabilitation work. Exotic fish species invasives. |  | 2012-02-22 | 2012-10-30 | 1 | 46000 | 2012-06-01 | Y | 0111 | FY2012 Watershed Transition Restoration Action Plan, Pass Creek, Gallatin NF | 2012-02-22 | Y | 6021.581 | 0.0061891 | 0.44573
Custer Gallatin National Forest | 100301010201 | Upper South Fork Sixteenmile Creek | Functioning Properly | 17124 | 64 | 36 | Poor | Good | Good | Good | Fair | Good | Poor | Fair | Good | Good | Good | Good | 2014 | <Principal_Reason><Concerns><Concern><Value>Invasive Species</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | Invasive aquatice species, fish passage issues, water quality impacts from roads, tree mortality from insects, non-navite grasses and noxious weeds. | <Known_Partners><Partner><Name>Montana Fish Wildlife and Parks</Name><Type>Known</Type></Partner><Partner><Name>US Fish and Widlife Service</Name><Type>Known</Type></Partner><Partner><Name>Northwest Energy</Name><Type>Known</Type></Partner><Partner><Name> | 2014-07-03 | 2016-09-30 | 5 | 365000 | 2016-09-10 | Y | 0111 | Upper South Fork Sixteenmile Creek WRAP | 2014-07-03 | Y | 10930.99 | 0.0080511 | 0.47396
Custer Gallatin National Forest | 100901020406 | O'Dell Creek | Functioning Properly | 29692 | 88 | 12 | Fair | Fair | Good | Fair | Fair | Good | Good | Fair | Poor | Good | Good | Good | 2015 | <Principal_Reason><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Maintain Condition</Value></Opportunity><Opportunity><Value>Potential Partnership</Value></Opportunity></Opportunities><Cost>$100,000 to $1 mil | Odell Creek watershed is an important watershed for riparian and aquatic habitats in the Great Plains Ecoregion of the Custer Gallatin National Forest. This watershed was identified as having native fish's and opportunity for restoration activites with | <Known_Partners><Partner><Name>National Wild Turkey Federation</Name><Type>Known</Type></Partner><Partner><Name>US Fish and Wildlife Service</Name><Type>Known</Type></Partner></Known_Partners> | 2015-07-06 | 2018-09-01 | 6 | 273000 | 2017-12-09 | Y | 0111 |  | 2015-07-06 |  | 26079.865 | 0.013805 | 0.65313
Custer Gallatin National Forest | 100901020601 | Upper Beaver Creek | Functioning at Risk | 14297.5 | 87 | 13 | Fair | Fair | Good | Fair | Fair | Fair | Fair | Good | Poor | Good | Good | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Water Quantity</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restorat | Riparian vegetation and channel conditions area at-risk and non-functioning due partly to livestock grazing. Some localized road drainage and water quality problems. Heavy fuels - FRCC rating of at risk. minimal perennial streamflow flow which could be i |  | 2011-09-28 | 2015-09-30 | 6 | 565000 | 2015-09-30 | Y | 0111 | Beaver Creek FY2011 Transition Watershed Restoration Action Plan | 2011-09-28 | Y | 12426.532 | 0.0066811 | 0.40782
Dakota Prairie Grasslands | 101303010603 | Giles Creek-North Fork Grand River | Functioning Properly | 16593 | 31 | 69 | Fair | Good | Good | Good | Fair | Poor | Good | Good | ---- | Good | Fair | Fair | 2011 | <Principal_Reason><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Maintain Condition</Value></Opportunity><Opportunity><Value>Potential Partnership</Value></Opportunity></Opportunities><Cost>$100,000 to $1 mil | Segments of Giles Creek and riparian areas are not in Proper Functioning Condition. There is not enough late seral native vegetation to support habitat requirements for Management Indicator Species and Sensitive Species. Expansion and invasion of undesi | <Known_Partners><Partner><Name>Grand River Cooperative Grazing Associat</Name><Type>Known</Type></Partner><Partner><Name>National Wild Turkey Federation</Name><Type>Known</Type></Partner><Partner><Name>North Dakota State University</Name><Type>Known</Type | 2011-10-25 | 2017-12-31 | 5 | 360000 | 2013-09-30 | Y | 0118 | Giles Creek - North Fork Grand River Watershed Restoration Action Plan | 2011-10-25 | Y | 5147.291 | 0.0077753 | 0.59289
Pike-San Isabel National Forest | 101900020104 | West Creek | Impaired Function | 44280.2 | 88 | 12 | Poor | Fair | Poor | Fair | Poor | Fair | Poor | Poor | Poor | Good | Poor | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restora | This watershed is a priority watershed for restoration due to the disproportionate amount of sediment being produced post 2002 Hayman wildfire. A portion of this watershed is targeted for restoration starting in 2011. The watershed is 303(d) listed for | <Known_Partners><Partner><Name>National Forest Foundation</Name><Type>Known</Type></Partner><Partner><Name>West Creek Water Users Association</Name><Type>Known</Type></Partner><Partner><Name>Youth Conservation Corps</Name><Type>Known</Type></Partner><Part |  | 2014-12-01 |  | 1390000 | 2014-09-30 | Y | 0212 | West Creek - 101900020104 |  | Y | 38967.712 | 0.018652 | 0.82548
Ouachita National Forest | 111401080305 | Holly Creek Mountain Fork | Functioning at Risk | 32212.6 | 52 | 48 | Good | Fair | Fair | Poor | Fair | Fair | Fair | Poor | Good | Good | Fair | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Municipal Watershed</Value></Resource><Resource><Value>Outstanding Resource Water</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Specie | The NFS lands within these watersheds were acquired in a land exchange with Weyerhaeuser in the 1990’s. Road densities are high and road maintenance has been neglected. In addition, recreation use in the form of OHVs has exploded. Road condition survey | <Known_Partners><Partner><Name>McCurtain County Commissioners</Name><Type>Known</Type></Partner><Partner><Name>Ok Dept of Conservation</Name><Type>Known</Type></Partner></Known_Partners> | 2011-09-29 | 2012-10-01 | 1 | 385000 | 2012-09-30 | Y | 0809 | Holly Creek Mountain Fork and Carter Creek Priority Watershed Restoration Plan | 2011-09-29 |  | 16676.936 | 0.012759 | 0.83482
Prescott National Forest | 150602020703 | Black Canyon | Functioning at Risk | 15451.3 | 98 | 2 | Fair | Fair | Good | Good | Poor | Poor | Poor | Fair | Good | Good | Good | Poor | 2012 | <Principal_Reason><Concerns><Concern><Value>Wildfire Risk</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Riparian Structure and Function</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restorati | Primary concerns within the watershed are related to soil and water resources and their influence on the Verde River system. Water quality issues within the watershed are sedimentation associated with inherently unstable limestone and lacustrine parent m | <Known_Partners><Partner><Name>Youth Conservation Corps</Name><Type>Known</Type></Partner><Partner><Name>Arizona State Parks</Name><Type>Known</Type></Partner></Known_Partners> | 2012-09-20 | 2018-09-30 | 30 | 1147735 | 2016-09-30 | Y | 0309 | Watershed Restoration Action Plan, Verde District, Prescott National Forest, Black Canyon Watershed | 2012-09-20 | Y | 15081.129 | 0.0061566 | 0.5097
Ashley National Forest | 140600030704 | Swift Creek | Functioning at Risk | 18153.5 | 100 | 0 | Fair | Good | Good | Fair | Good | Poor | Poor | Fair | Good | Fair | Good | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Wildfire Risk</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity | Erosion related issues associated with system trails in this High Uintas Wilderness watershed. Primary concern is with a seven mile long primitive road segment in the watershed created prior to wilderness designation. This road was used to transport hea |  | 2011-10-25 | 2014-09-30 | 3 | 137000 | 2014-09-27 | Y | 0401 | Swift Creek WRAP | 2011-10-25 |  | 18153.469 | 0.0078247 | 0.43172
Helena National Forest | 170102030103 | Copper Creek | Functioning at Risk | 26015.9 | 97 | 3 | Good | Fair | Good | Fair | Fair | Poor | Fair | Fair | Poor | Good | Fair | Fair | 2011 | <Principal_Reason><Resources><Resource><Value>Species Protection Area</Value></Resource></Resources><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Potential Partnership</Value></Opportunity></Opportunities></ | Critical Bull Trout habitat; decisions in place to accomplish significant work in 2012-13. | <Known_Partners><Partner><Name>Trout Unlimited (Big Blackfoot Chapter)</Name><Type>Known</Type></Partner><Partner><Name>Montana Trail Riders Assoc./Great Falls </Name><Type>Known</Type></Partner><Partner><Name>High Divide Trails Alliance/Montana Wild</Nam | 2011-10-27 | 2013-10-31 | 4 | 448000 | 2013-09-30 | Y | 0112 | Copper Creek Watershed Restoration Action Plan | 2011-10-27 | Y | 25198.713 | 0.01247 | 0.6959
Mt Baker-Snoqualmie National Forest | 171100090302 | Upper South Fork Skykomish River | Functioning Properly | 28235.2 | 82 | 18 | Good | Good | Good | Good | Fair | Fair | Fair | Good | Good | Good | Good | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Species Protection Area</Value></Resource></Resources><Cost>$100,000 to $1 million</Cost></Principal_Reason> | The Upper South Fork Skykomish River serves as crtitical refugia for maintaining and recovering at risk stocks of Chinook salmon, bull trout and steelhead. | <Known_Partners><Partner><Name>Town of Skykomish</Name><Type>Known</Type></Partner></Known_Partners> | 2011-09-01 | 2016-09-01 | 3 | 1000000 | 2015-09-01 | Y | 0605 | Upper South Fork Skykomish River Watershed Restoration Action Plan | 2011-09-01 | Y | 23123.253 | 0.013695 | 0.76174
Willamette National Forest | 170900010105 | Staley Creek | Functioning at Risk | 26086.7 | 99 | 1 | Poor | Fair | Good | Good | Poor | Poor | Good | Good | Good | Good | Good | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</V | Rationale for priority selection: One of 11 sub-watersheds of the Upper Middle Fork Willamette deemed the highest restoration priority area for terrestrial and aquatic restoration on the Willamette NF (2005); - includes some of the last high priority roa | <Known_Partners><Partner><Name>Middle Fork Willamette Watershed Council</Name><Type>Known</Type></Partner><Partner><Name>Northwest Youth Corps</Name><Type>Known</Type></Partner><Partner><Name>Oregon Watershed Enhancement Board</Name><Type>Known</Type></Pa | 2011-09-30 | 2017-09-30 | 4 | 398500 | 2017-08-18 | Y | 0618 | Staley Creek Watershed Restoration Action Plan | 2011-09-30 | Y | 25931.521 | 0.011677 | 0.54515
Tahoe National Forest | 180201280403 | Peavine Creek-North Fork Middle Fork American River | Functioning Properly | 21581.9 | 92 | 8 | Fair | Good | Good | Good | Fair | Fair | Good | Fair | Good | Fair | Good | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Wildfire Risk</Value></Concern></Concerns><Opportunities><Opportunity><Value>Maintain Condition</Value></Opportunity></Opportunities></Principal_Reason> | Prior investment in watershed protection. Ability to capitalize on current project planning. Protection of water quality in municipal water supply and hydropower production watershed. |  | 2011-09-30 | 2015-09-30 | 5 | 4075000 | 2015-09-15 | Y | 0517 | Peavine Creek North Fork Middle Fork American River Watershed Restoration Action Plan | 2011-09-30 | Y | 19783.634 | 0.0091044 | 0.63034
White Mountain National Forest | 010801030401 | Headwaters Ammonoosuc River | Functioning Properly | 21562.7 | 97 | 4 | Fair | Good | Poor | Good | Good | Fair | Fair | Fair | Good | Good | Good | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</V | An integrated resources management analysis identified opportunites to improve the condition of this watershed. A suite of trail relocation, road decommissioning and road maintenance activities, accompanied by riparian restoration will help balance recrea | <Known_Partners><Partner><Name>Ammonoosuc River LAC</Name><Type>Known</Type></Partner><Partner><Name>New Hampshire Fish and Game</Name><Type>Known</Type></Partner><Partner><Name>Bretton Woods Ski Area</Name><Type>Known</Type></Partner><Partner><Name>Appal | 2011-09-30 | 2017-09-30 | 8 | 427000 | 2017-09-30 | Y | 0922 | Headwaters Ammonoosuc River Watershed Restoration Action Plan | 2011-09-30 | Y | 20800.237 | 0.0098264 | 0.4841
Daniel Boone National Forest | 051002040209 | Indian Creek-Red River | Functioning Properly | 37002.1 | 56 | 44 | Good | Good | Fair | Good | Fair | Poor | Fair | Fair | Good | Good | Poor | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Outstanding Resource Water</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Quality</ | This watershed was chosen because it is one of the four watersheds where we have multiple issues that are being addressed by a collaborative Watershed Protection Plan. | <Known_Partners><Partner><Name>Kentucky Division of Water</Name><Type>Known</Type></Partner><Partner><Name>Kentucky Department of Fish and Wildlife</Name><Type>Known</Type></Partner><Partner><Name>Kentucky Waterways Alliance</Name><Type>Known</Type></Part | 2011-09-30 | 2016-12-31 | 3 | 50000 | 2015-12-28 | Y | 0802 | Red River Gorge Watershed Protection Plan | 2011-09-30 | Y | 20558.057 | 0.015334 | 0.88698
Gila National Forest | 150400040604 | Vigil Canyon | Functioning Properly | 25992 | 98 | 2 | Fair | Good | Good | Good | Fair | Fair | Poor | Fair | Good | Good | Good | Fair | 2015 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</V | Vigil Canyon watershed contains Vigil springs which has perennial water and is the only riparian/wetland area that has the potential to support both woody and herbaceous components. It is also upstream of the South Dugway-San Francisco River watershed, a | <Known_Partners><Partner><Name>Grazing permittees</Name><Type>Known</Type></Partner><Partner><Name>Arizona State University</Name><Type>Known</Type></Partner><Partner><Name>New Mexico Environment Dept.</Name><Type>Known</Type></Partner></Known_Partners> | 2015-01-15 | 2019-09-30 | 1 | 125000 | 2016-08-30 | Y | 0306 | Vigil Canyon 6th Code Watershed Restoration Action Plan | 2015-01-15 | Y | 25549.25 | 0.010145 | 0.57369
Uinta-Wasatch-Cache National Forest | 160102030206 | Saddle Creek | Functioning at Risk | 30880.7 | 68 | 32 | Fair | Fair | Good | Fair | Fair | Poor | Poor | Fair | Good | Good | Good | Fair | 2014 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | Soil loss, water quality conditions, and species habitat can improved through access management and restoration of existing conditions. | <Known_Partners><Partner><Name>UT Partners for Conservation Development</Name><Type>Known</Type></Partner><Partner><Name>Sportsman for Fish and Wildlife</Name><Type>Known</Type></Partner><Partner><Name>Ruby Pipeline </Name><Type>Known</Type></Partner><Par | 2014-05-05 | 2015-09-30 | 3 | 290000 | 2015-09-30 | Y | 0419 | Saddle Creek Restoration Plan | 2014-05-05 | Y | 20969.977 | 0.013526 | 0.63196
Coconino National Forest | 150200080304 | Barbershop Canyon | Functioning at Risk | 13447.3 | 100 | 0 | Poor | Poor | Good | Good | Fair | Poor | Good | Poor | Good | Fair | Fair | Good | 2011 | <Principal_Reason><Resources><Resource><Value>Other</Value></Resource><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Wildfire Risk</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern | Ability to improve overall watershed condition from Functioning at Risk to Functioning Properly with current NEPA decisions ripe for implementation. Several key watershed improvement projects identified, shovel ready, including timber stand improvement, | <Known_Partners><Partner><Name>AZ Game and Fish</Name><Type>Known</Type></Partner><Partner><Name>Grand canyon Wildlands Council</Name><Type>Known</Type></Partner><Partner><Name>US Fish and Wildlife Service</Name><Type>Known</Type></Partner><Partner><Name> | 2011-09-21 | 2014-09-30 | 5 | 338750 | 2013-09-30 | Y | 0304 | Barbershop Canyon Watershed Restoration Action Plan | 2011-09-21 | Y | 13406.385 | 0.0053302 | 0.41282
Idaho Panhandle National Forest | 170103010601 | Iron Creek-Little North Fork Coeur d'Alene River | Functioning at Risk | 28427.1 | 99 | 1 | Good | Poor | Poor | Good | Fair | Fair | Fair | Fair | Fair | Good | Fair | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restora | The ecological condition of the subwatershed has been altered as a result of resource extraction and extensive human use over the last 100 years. Anthropogenic influences include current and historic mining, timber harvest, livestock grazing, and historic |  | 2011-11-17 | 2014-10-01 | 4 | 1825000 | 2014-10-01 | Y | 0104 | Iron Creek - 2011 Watershed Restoration Action Plan | 2011-11-17 | Y | 28236.76 | 0.013823 | 0.5426
Idaho Panhandle National Forest | 170103040304 | Bruin Creek-St Joe River | Functioning at Risk | 27521.1 | 100 | 0 | Fair | Fair | Fair | Good | Fair | Poor | Good | Fair | Fair | Good | Fair | Good | 2011 | <Principal_Reason><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Opportunity><Opportunity><Value>Socio-Economic Benefit</Value></Opportunity><Opportunity><Value>Improve Condition</Value></Opportunity></Opportunities><Cost>&lt; $100,0 | Watershed is a stronghold for native fish habitat and populations. Reducing road densities would improve water quality by reducing sediment inputs to streams and would reduce risk of future road or culver failures that could further impair the ecosystem. |  | 2011-11-03 | 2015-01-01 | 1 | 309000 | 2014-09-30 | Y | 0104 | Bruin Creek 2011 Watershed Action Plan | 2011-11-03 | Y | 27413.927 | 0.013214 | 0.77147
Six Rivers National Forest | 180102090804 | Bluff Creek | Functioning Properly | 47402 | 98 | 2 | Good | Good | Fair | Good | Fair | Fair | Good | Poor | Good | Good | Fair | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Other</Value></Concern><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Wildfire Risk</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restoration</Valu | Part of a larger scale road restoration project in the Lower Middle Klamath watershed. Current Partnership with Karuk Tribe allows the FS to leverage matching funds from internal and external sources. There are 19 miles of prime anadromous habitat in Bl | <Known_Partners><Partner><Name>Karuk Tribe</Name><Type>Known</Type></Partner><Partner><Name>Yurok Tribe</Name><Type>Known</Type></Partner><Partner><Name>Mid Klamath Watershed Restoration Center</Name><Type>Known</Type></Partner></Known_Partners> | 2016-02-29 | 2016-02-29 | 0 | 0 | 2016-02-29 | Y | 0510 | Bluff Creek Watershed Restoration Action Plan | 2016-02-29 | Y | 46495.836 | 0.020672 | 0.84272
Boise National Forest | 170602080403 | Stolle Creek-South Fork Salmon River | Functioning Properly | 20201.6 | 100 | 0 | Fair | Fair | Fair | Good | Good | Fair | Good | Good | Fair | Good | Fair | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restora | The key concern is elevated sediment in stream channels, where the mainstem SFSR is 303(d) listed for sediment with a total maximum daily load (TMDL) approved in 1991, the nation’s first non-point source TMDL. A secondary concern is water temperature and |  | 2011-09-30 | 2017-09-30 | 5 | 3760000 | 2015-09-30 | Y | 0402 |  | 2011-09-30 |  | 20201.577 | 0.0092658 | 0.56
Salmon-Challis National Forest | 170402180101 | Upper Star Hope Creek | Functioning Properly | 21175.8 | 100 | 1 | Fair | Fair | Good | Good | Good | Fair | Good | Poor | Good | Fair | Good | Fair | 2011 | <Principal_Reason><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Maintain Condition</Value></Opportunity></Opportunities><Cost>$100,000 to $1 million</Cost></Principal_Reason> | The Upper Star Hope Creek 6th-level watershed, located in the East Fork Big Lost River drainage about 20 miles Southwest of Mackay, Idaho, was identified as a Class 2 (functioning at risk) watershed during the 2011 Watershed Condition Classification Asses |  | 2012-10-01 | 2016-09-30 | 4 | 103000 | 2016-09-30 | Y | 0413 | Watershed Restoration Action Plan and Completion Report for the Upper Star Hope Creek Watershed | 2012-10-01 | Y | 21070.791 | 0.0095706 | 0.4823
Rogue River-Siskiyou National Forests | 171003050201 | Headwaters South Fork Coquille River | Functioning at Risk | 40183.6 | 75 | 25 | Good | Fair | Poor | Good | Fair | Poor | Good | Poor | Good | Good | Fair | Good | 2007 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | The South Fork Coquille River watershed was selected as a priority watershed on the Rogue River-Siskiyou National Forest, due to its resource value and restoration potential for fisheries, water, and wildlife value. | <Known_Partners><Partner><Name>Coquille Watershed Association</Name><Type>Known</Type></Partner><Partner><Name>OWEB</Name><Type>Known</Type></Partner><Partner><Name>WWRI/Ecotrust</Name><Type>Known</Type></Partner></Known_Partners> | 2007-08-13 |  | 6 | 1231500 | 2012-09-15 | Y | 0610 | South Fork Coquille Watershed Aquatic Restoration Plan | 2007-08-13 | Y | 30134.28 | 0.01789 | 1.0008
National Forests In Alabama | 031601100201 | Rush Creek-Brushy Creek | Functioning Properly | 38292.1 | 87 | 14 | Good | Good | Good | Good | Good | Fair | Fair | Good | Good | Good | Good | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Water Quality</Value></Concern><Concern><Value>Species Habitat</Value></Concern></Concerns></Principal_Reason> | Maintain water quality forT&E aquatic habitat. Currently roads and horse trails are in a degrading condition producing sediment to waterways above past levels. | <Known_Partners><Partner><Name>Alabama Natural Heritage Program</Name><Type>Known</Type></Partner><Partner><Name>Backcountry Horsemen of Alabama</Name><Type>Known</Type></Partner><Partner><Name>Alabama A&amp;M University</Name><Type>Known</Type></Partner> | 2011-09-30 | 2016-09-30 | 6 | 4250905 | 2017-09-30 | Y | 0801 | RushCreek-Brushy Creek Watershed Restoration Action Plan | 2011-09-30 |  | 33112.853 | 0.015168 | 0.62833
Huron Manistee National Forest | 040601010803 | Osborn Creek-North Branch White River | Functioning Properly | 14522.8 | 8 | 92 | Fair | Fair | Good | Good | Good | Fair | Good | Fair | Good | Fair | Fair | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Water Quality</Value></Concern><Concern><Value>Species Habitat</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Non-NFS Land Collaboration | This watershed contains high priority aquatic resources in an ecologically sensitive part of the Mansistee National Forest. A strong partnership already exists within the watershed. The Huron-Manistee National Forests are an active member of this partners | <Known_Partners><Partner><Name>MI DEQ</Name><Type>Known</Type></Partner><Partner><Name>National Forest Foundation</Name><Type>Known</Type></Partner><Partner><Name>Coca Cola Company</Name><Type>Known</Type></Partner><Partner><Name>Great Lakes Fisheries Tru | 2011-09-30 | 2016-09-30 | 5 | 342489 | 2013-07-01 | Y | 0904 | Osborne Creek - North Branch White River Watershed Restoration Action Plan | 2011-09-30 | Y | 1153.151 | 0.006555 | 0.6462
Shoshone National Forest | 100700060106 | Squaw Creek-Clarks Fork Yellowstone River | Functioning at Risk | 22727.4 | 95 | 5 | Poor | Good | Fair | Good | Fair | Fair | Good | Fair | Good | Good | Good | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Wildfire Risk</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Oppo | Watershed was selected based upon three criteria. 1) NEPA cleared projects were being implemented or were ready to implement in 2011 that addressed indicators classified as 2 or 3. 2) Watershed was a yellow watershed. 3) Projects have potential to move wa | <Known_Partners><Partner><Name>Montana Conservation Corps</Name><Type>Known</Type></Partner></Known_Partners> | 2012-02-10 | 2016-09-30 | 17 | 117100 | 2016-09-30 | Y | 0214 | FY2011 Transition WATERSHED RESTORATION ACTION PLAN CLARKS FORK YELLOWSTONE RIVER-SQUAW CREEK 100700060106 | 2012-02-10 | Y | 21665.337 | 0.010482 | 0.83346
Black Hills National Forest | 101201090802 | Iron Creek | Functioning at Risk | 12174.7 | 76 | 25 | Poor | Fair | Good | Good | Fair | Fair | Fair | Fair | Good | Good | Good | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Other</Value></Resource></Resources><Cost>$1 million to $5 million</Cost></Principal_Reason> | After considering various watersheds the Black Hills National Forest (NF) chose the Iron Creek Watershed as a priority watershed for the 2011 selection process. The Watershed Conservation Framework provided guidance for selecting priority watersheds. Spe | <Known_Partners><Partner><Name>South Dakota Game, Fish and Parks</Name><Type>Known</Type></Partner><Partner><Name>Pennington County Resource Advisory Comm</Name><Type>Known</Type></Partner><Partner><Name>Custer County Conservation District</Name><Type>Kno | 2011-10-17 | 2016-09-30 | 13 | 1990158 | 2017-11-06 | Y | 0203 | Iron Creek Watershed Restoration Action Plan | 2011-10-17 | Y | 9186.677 | 0.0055131 | 0.57319
Lewis And Clark National Forest | 100302010104 | Lower South Fork Two Medicine River | Functioning at Risk | 42992.3 | 43 | 57 | Poor | Fair | Good | Good | Good | Good | Poor | Poor | Poor | Good | Poor | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Invasive Species</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</ | The Lower South Fork Two Medicine River is a unique watershed located just south of Glacier National Park and west of the Black Feet Indian Reservation. The watershed is host to a high biological diversity of wildlife species including grizzly bear, timbe | <Known_Partners><Partner><Name>Montana Fish Wildlife and Parks</Name><Type>Known</Type></Partner></Known_Partners> | 2013-10-31 | 2015-10-01 | 3 | 95000 | 2014-09-30 | Y | 0115 | Lower South Fork Two Medicine Watershed Restoration Action Plan | 2013-10-31 | Y | 18418.769 | 0.021115 | 0.89793
Ozark-St Francis National Forest | 110100010102 | Fleming Creek-White River | Functioning Properly | 18918.8 | 58 | 42 | Good | Good | Good | Good | Good | Fair | Good | Fair | Good | Good | Fair | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Other</Value></Resource><Resource><Value>Outstanding Resource Water</Value></Resource><Resource><Value>Municipal Watershed</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Functio | This watershed was selected due the presence of three Aquatic Organism Passage issues to be corrected, the presence of the Long Nose Darter and the crayfish Orconectes williamsi, both Regional Forester's Sensitive Species and Species of Concern in Arkansa | <Known_Partners><Partner><Name>U.S. Fish and Wildlife Service</Name><Type>Known</Type></Partner><Partner><Name>Madison and Franklin County governments</Name><Type>Known</Type></Partner><Partner><Name>Center for Aquatic Technology Transfer</Name><Type>Know | 2011-10-20 | 2016-10-01 | 4 | 1398950 | 2014-03-25 | Y | 0810 | Fleming Creek Watershed Restoration Action Plan | 2011-10-20 | Y | 11008.217 | 0.0076328 | 0.4876
Ouachita National Forest | 111401070207 | Carter Creek | Functioning Properly | 18873.7 | 35 | 65 | Good | Fair | Good | Good | Fair | Fair | Good | Fair | Good | Good | Fair | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Wild and Scenic River</Value></Resource><Resource><Value>Species Protection Area</Value></Resource><Resource><Value>Outstanding Resource Water</Value></Resource></Resources><Concerns><Concern><Value>Riparian S | The NFS lands within these watersheds were acquired in a land exchange with Weyerhaeuser in the 1990’s. Road densities are high and road maintenance has been neglected. In addition, recreation use in the form of OHVs has exploded. Road condition survey | <Known_Partners><Partner><Name>OK Dept Wildlife Conservation</Name><Type>Known</Type></Partner><Partner><Name>McCurtain County commissioners</Name><Type>Known</Type></Partner><Partner><Name>US Fish and Wildlife Service</Name><Type>Known</Type></Partner></ | 2010-09-29 | 2012-10-01 | 1 | 400000 | 2012-09-30 | Y | 0809 | Holly Creek Mountain Fork and Carter Creek Priority Watershed Restoration | 2010-09-29 |  | 6678.833 | 0.0074758 | 0.49248
Carson National Forest | 140801030405 | Martinez Canyon-Carrizo Canyon | Functioning Properly | 35993.7 | 8 | 92 | Good | Good | Good | Fair | Fair | Fair | Poor | Fair | Good | Good | Fair | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Invasive Species</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Opportunity><Opportunity><Value> | Added to Forest priority to allow for development of WRAP in conjunction with Ciruelas Canyon - Arroyo Companero (HUC 140801030403) and on-going landscape analysis for Carrizo Canyon 5th code Watershed (HUC 1408010304) with other partners. | <Known_Partners><Partner><Name>BLM</Name><Type>Known</Type></Partner><Partner><Name>Oil and Gas Companies</Name><Type>Known</Type></Partner><Partner><Name>BLM/FS permittee</Name><Type>Known</Type></Partner><Partner><Name>NRCS</Name><Type>Known</Type></Par | 2011-12-21 | 2016-09-30 | 8 | 115000 | 2017-09-30 | Y | 0302 | Watershed Restoration Action Plan for Ciruelas Canyon - Arroyo Companero and NFS portion of Martinez Canyon - Carrizo Canyon | 2011-12-21 |  | 2796.932 | 0.014661 | 0.66246
Idaho Panhandle National Forest | 170102131202 | Middle Lightning Creek | Functioning at Risk | 28131.8 | 100 | 0 | Fair | Fair | Poor | Good | Poor | Good | Good | Good | Fair | Good | Fair | Good | 2014 | <Principal_Reason><Concerns><Concern><Value>Other</Value></Concern><Concern><Value>Water Quality</Value></Concern><Concern><Value>Riparian Structure and Function</Value></Concern></Concerns><Cost>$100,000 to $1 million</Cost></Principal_Reason> | Increased road density, roads in floodplain, reduced aquatic and ripariant habitat complexity, elevated stream temps | <Known_Partners><Partner><Name>Avista</Name><Type>Known</Type></Partner><Partner><Name>Trout Unlimited</Name><Type>Known</Type></Partner><Partner><Name>National Forest Foundation</Name><Type>Known</Type></Partner><Partner><Name>Friends of Scotchman Peaks | 2013-12-17 | 2016-09-30 | 2 | 210000 | 2015-10-31 | Y | 0104 | Lower and Middle Lighning Creek WRAP | 2013-12-17 | Y | 28131.801 | 0.013797 | 0.55255
Caribou-Targhee National Forest | 170401050308 | Jackknife Creek | Functioning at Risk | 30424.4 | 95 | 5 | Fair | Fair | Fair | Good | Fair | Fair | Good | Good | Fair | Good | Good | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Water Quality</Value></Concern><Concern><Value>Species Habitat</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Non-NFS Land Collaboration | Jackknife Creek is an important Yellowstone cutthroat fisheries stronghold providing critical habitat. Stream conditions and functions are classified as fair and could be improved both on FS and private lands. Efforts have been underway to improve these |  | 2011-09-26 | 2015-09-30 | 5 | 1050000 | 2014-09-30 | Y | 0415 |  | 2011-09-26 | Y | 28844.861 | 0.013605 | 0.65705
Mendocino National Forest | 180101040503 | Thatcher Creek | Functioning Properly | 23195.1 | 79 | 21 | Good | Good | Fair | Good | Good | Good | Good | Fair | Good | Good | Good | Fair | 2011 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Water Quality</Value></Concern></Concerns></Principal_Reason> | Watershed is designated critical habitat for salmon and steelhead (ESA listed). Most of NFS land in watershed is in Yuki Wilderness. Unauthorized motorized use is causing erosion and sedimentation. | <Known_Partners><Partner><Name>California State Parks OHV Division</Name><Type>Known</Type></Partner></Known_Partners> | 2011-01-01 | 2012-09-30 | 2 | 95000 | 2012-09-30 |  | 0508 | Thatcher Creek | 2011-01-01 | Y | 18295.312 | 0.0098062 | 0.4705
Rogue River-Siskiyou National Forests | 171003110203 | Grayback Creek | Functioning Properly | 15566.2 | 82 | 18 | Good | Fair | Good | Good | Good | Fair | Good | Fair | Good | Good | Fair | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</V | Key issues within this subwatershed are fine sediment in stream channels, high surface water temperature, and salmon habitat simplification. SONNC coho salmon are present within the subwatershed and are listed as threatened under the Endangered Species A | <Known_Partners><Partner><Name>Illinois Valley Watershed Council</Name><Type>Known</Type></Partner><Partner><Name>Lomakatsi Restoration Project</Name><Type>Known</Type></Partner><Partner><Name>Oregon Department of Fish and Wildlife</Name><Type>Known</Type | 2011-09-17 | 2018-12-31 | 2 | 2926000 | 2017-07-26 | Y | 0610 | Sucker Creek Watershed FY2011 Transition Watershed Restoration Action Plan | 2011-09-17 | Y | 12753.919 | 0.0068596 | 0.4157
Tongass National Forest | 190101030501 | Twelvemile Creek | Functioning Properly | 12842.1 | 71 | 30 | Good | Poor | Good | Good | Poor | Fair | Good | Good | Good | Good | Good | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Opportunity><Opportunity><Value>P | Aquatic habitat indicators and road density and proximity indicators all rate as 'Impaired' function. Deficient large wood supply and young growth riparain zones and low pool counts, channel and widening have diminished fish habitat. High road desnity has | <Known_Partners><Partner><Name>National Forest Foundation</Name><Type>Known</Type></Partner><Partner><Name>Prince of Wales Resource Advisory Commit</Name><Type>Known</Type></Partner><Partner><Name>FishAmerica Foundation</Name><Type>Known</Type></Partner>< | 2011-07-14 | 2013-09-30 | 5 | 656600 | 2013-08-23 | Y | 1005 | FY2011 Transition Watershed Restoration Action Plan, Craig Ranger District, Tongass National Forest | 2011-07-14 | Y | 9058.741 | 0.0073502 | 0.54624
National Forests In Florida | 031102010701 | Impassable Bay | Functioning at Risk | 31459 | 94 | 6 | Fair | Fair | Fair | Fair | Poor | Poor | Fair | Fair | Poor | Fair | Good | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Species Protection Area</Value></Resource><Resource><Value>Municipal Watershed</Value></Resource></Resources><Concerns><Concern><Value>Wildfire Risk</Value></Conce | This watershed has a history of severe wildfires (2004 Impassable Bay; 2007 Bugaboo; 2011 Impassible Bay) which not only impact upland and swamp ecosystems (loss of timber, habitat for T&E species, etc.) but can also severely effect watershed health due t |  | 2011-09-30 | 2014-09-30 | 5 | 286125 | 2018-02-27 | Y | 0805 | FY2011 Transition Watershed Restoration Action Plan | 2011-09-30 | Y | 29637.661 | 0.011948 | 0.6455
Carson National Forest | 140801030404 | Munoz Creek | Functioning Properly | 20066.7 | 21 | 79 | Good | Good | Good | Good | Good | Good | Fair | Fair | Good | Good | Good | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Invasive Species</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Opportunity><Opportunity><Value> | Added to Forest priority to allow for development of WRAP in conjunction with Ciruelas Canyon - Arroyo Companero (HUC 140801030403) and on-going landscape analysis for Carizzo Canyon 5th code WS (HUC 1408010304) with other partners. | <Known_Partners><Partner><Name>BLM - Farmington Field Office</Name><Type>Known</Type></Partner><Partner><Name>BLM/FS Permittee</Name><Type>Known</Type></Partner><Partner><Name>BIA Jicarilla Tribe </Name><Type>Known</Type></Partner><Partner><Name>NRCS</Nam | 2011-12-21 | 2016-09-30 | 4 | 60000 | 2016-09-30 | Y | 0302 | Watershed Restoration Action Plan for Ciruelas Canyon - Arroyo Companero and NFS portion of Munoz Creek | 2011-12-21 | Y | 4297.966 | 0.0081809 | 0.57782
Colville National Forest | 170102160303 | East Branch Le Clerc Creek | Functioning Properly | 26592.4 | 42 | 58 | Fair | Fair | Good | Good | Good | Fair | Good | Fair | Good | Good | Good | Good | 2011 | <Principal_Reason><Resources><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</ | Bull Trout Critical Habitat | <Known_Partners><Partner><Name>WDFW</Name><Type>Known</Type></Partner><Partner><Name>Stimson Lumber Company</Name><Type>Known</Type></Partner><Partner><Name>Pend Oreille Public Utility Department </Name><Type>Known</Type></Partner><Partner><Name>Kalispell | 2011-09-01 | 2016-09-20 | 8 | 1627039 | 2016-09-20 | Y | 0621 | East Branch LeClerc TWRAP | 2011-09-01 | Y | 11152.116 | 0.013156 | 0.56373
Bitterroot National Forest | 170102050702 | Upper Sleeping Child Creek | Functioning at Risk | 9890.8 | 100 | 0 | Fair | Fair | Fair | Good | Good | Poor | Good | Fair | Good | Good | Fair | Fair | 2011 | <Principal_Reason><Concerns><Concern><Value>Invasive Species</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></O | The Upper Sleeping Child watershed is located within the Darby Lumber Lands project area and is one the highest priorities for watershed rehabilitation on the forest. Upper Sleeping Child contains several sections of former private “checkerboard” section | <Known_Partners><Partner><Name>Trout Unlimited</Name><Type>Known</Type></Partner><Partner><Name>Ravalli County Off Road Users Associatio</Name><Type>Known</Type></Partner><Partner><Name>Bitterroot Water Forum</Name><Type>Known</Type></Partner></Known_Part | 2011-10-28 | 2015-09-30 | 2 | 120000 | 2015-09-30 | Y | 0103 | Upper Sleeping Child Watershed Restoration Action Plan | 2011-10-28 | Y | 9872.38 | 0.0046517 | 0.48167
Olympic National Forest | 171100170102 | Lower South Fork Skokomish River | Functioning at Risk | 27531.7 | 58 | 42 | Fair | Good | Fair | Good | Fair | Fair | Good | Good | Good | Good | Good | ---- | 2007 | <Principal_Reason><Opportunities><Opportunity><Value>Larger-Scale Restoration</Value></Opportunity><Opportunity><Value>Potential Partnership</Value></Opportunity><Opportunity><Value>Improve Condition</Value></Opportunity></Opportunities><Cost>$5 million t | One of the Forest's best opportunities to recovery listed bull trout, and link in with a highly functioning and effect collaborative restoration group, Skokomish Watershed Action Team; extensive restoration opportunities in the subwatershed. | <Known_Partners><Partner><Name>Skokomish Watershed Action Team</Name><Type>Known</Type></Partner><Partner><Name>Skokomish Tribe</Name><Type>Known</Type></Partner></Known_Partners> | 2012-09-28 | 2016-09-30 | 7 | 8618000 | 2015-12-31 | Y | 0609 | Lower South Fork Skokomish River Watershed Restoration Action Plan | 2012-09-28 | Y | 16020.265 | 0.013347 | 0.62062
Columbia River Gorge National Scenic Area | 170800010804 | Latourell Creek-Columbia River | Functioning at Risk | 29606.3 | 12 | 89 | Fair | Good | Good | Fair | Poor | Poor | Good | Good | Good | Good | Fair | ---- | 2015 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity></Opportunities></Principal_Reason> | In 2002, the Lower Columbia Basin was assessed by the Pacific Northwest Region of the Forest Service and was determined to be one of the highest priority for restoration based on 1) Aquatic Resource Condition, 2) Watershed Sensitivity and 3) Management In | <Known_Partners><Partner><Name>Lower Columbia Estuary Partnership</Name><Type>Known</Type></Partner><Partner><Name>The Penstemon Fund</Name><Type>Known</Type></Partner><Partner><Name>The Oregon Watershed Enhancement Board</Name><Type>Known</Type></Partner | 2015-04-01 | 2016-12-15 | 1 |  | 2016-09-30 | Y | 0622 | Viento Creek and Latourell Creek - Columbia River | 2015-04-01 | Y | 3411.502 | 0.013845 | 0.69355
Salmon-Challis National Forest | 170602030702 | Moose Creek | Functioning Properly | 25359.7 | 100 | 0 | Good | Fair | Good | Good | Fair | Poor | Good | Fair | Good | Fair | Good | Fair | 2005 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restora | Watershed was selected as a priority prior to WCF effort. | <Known_Partners><Partner><Name>Lemhi County RAC</Name><Type>Known</Type></Partner></Known_Partners> |  | 2011-09-30 | 5 | 50000 | 2011-09-30 |  | 0413 | Moose Creek Watershed Assessment |  |  | 25320.464 | 0.011773 | 0.57436
Wallowa Whitman National Forest | 170601040501 | North Fork Catherine Creek | Functioning Properly | 21845.9 | 99 | 1 | Good | Good | Good | Good | Good | Poor | Good | Fair | Good | Good | Good | Good | 2013 | <Principal_Reason><Resources><Resource><Value>Species Protection Area</Value></Resource></Resources><Cost>$100,000 to $1 million</Cost></Principal_Reason> | Provides habitat for these ESA listed species: Bull Trout, Summer Steelhead, and Spring Chinook. | <Known_Partners><Partner><Name>Bonneville Power Administration</Name><Type>Known</Type></Partner><Partner><Name>Grande Ronde Model Watershed</Name><Type>Known</Type></Partner></Known_Partners> | 2013-02-26 | 2014-09-30 | 1 | 500000 | 2014-10-01 | Y | 0616 | Upper Catherine Creek Watershed TWRAP | 2013-02-26 | Y | 21615.604 | 0.010108 | 0.58439
Tongass National Forest | 190101030502 | Indian Creek-Harris River | Functioning Properly | 26030.3 | 86 | 14 | Good | Poor | Good | Good | Poor | Good | Good | Good | Good | Good | Good | ---- | 2000 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Larger-Scale Restora | Harris River has been a Tongass Focus Watershed for integrated watershed restoration work since 2000. | <Known_Partners><Partner><Name>The Nature Conservancy</Name><Type>Known</Type></Partner><Partner><Name>State of Alaska</Name><Type>Known</Type></Partner><Partner><Name>NOAA</Name><Type>Known</Type></Partner><Partner><Name>National Fish and Wildlife Founda | 2007-10-01 | 2011-09-30 | 3 | 3600000 | 2011-09-30 |  | 1005 | Harris River Restoration Plan | 2007-10-01 | Y | 22356.926 | 0.014972 | 0.84955
Daniel Boone National Forest | 051002040205 | Clifty Creek-Red River | Functioning at Risk | 17178.2 | 45 | 55 | Fair | Good | Fair | Good | Fair | Fair | Poor | Fair | Good | Good | Good | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Wilderness</Value></Resource><Resource><Value>Wild and Scenic River</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Quality</Value | This watershed was chosen because it is one of the four watersheds where we have multiple issues that are being addressed by a collaborative Watershed Protection Plan. | <Known_Partners><Partner><Name>Kentucky Division of Water</Name><Type>Known</Type></Partner><Partner><Name>Kentucky Department of Fish and Wildlife</Name><Type>Known</Type></Partner><Partner><Name>Kentucky Waterways Alliance</Name><Type>Known</Type></Part | 2011-09-30 | 2016-12-31 | 3 | 50000 | 2015-12-28 | Y | 0802 | Red River Gorge Watershed Protection Plan | 2011-09-30 | Y | 7793.602 | 0.0071135 | 0.62506
Ouachita National Forest | 080401010401 | Upper South Fork Ouachita River | Functioning Properly | 29628.4 | 83 | 17 | Good | Good | Fair | Good | Good | Poor | Good | Poor | Good | Good | Fair | ---- | 2015 | <Principal_Reason><Resources><Resource><Value>Municipal Watershed</Value></Resource><Resource><Value>Species Protection Area</Value></Resource></Resources><Cost>$100,000 to $1 million</Cost></Principal_Reason> | 1. To reduce the amount of soil erosion and sedimentation which is negatively affecting water quality and quantity and the natural hydrology of tributaries, and which is contributing to safety hazards on some roads used by the public. 2. To improve water | <Known_Partners><Partner><Name>Arkansas Game &amp; Fish Commission</Name><Type>Known</Type></Partner><Partner><Name>Arkansas State University</Name><Type>Known</Type></Partner><Partner><Name>Montgomery County</Name><Type>Known</Type></Partner></Known_Part | 2015-09-03 | 2018-09-30 | 3 | 400000 | 2018-01-01 | Y | 0809 | Watershed Restoration Action Plan (WRAP) for the Upper South Fork Ouachita River | 2015-09-03 |  | 24594.56 | 0.011773 | 0.58791
Pike-San Isabel National Forest | 110200010608 | Grays Creek-Poncha Creek | Functioning at Risk | 15697 | 75 | 25 | Poor | Fair | Good | Good | Poor | Fair | Good | Fair | Good | Good | Fair | Fair | 2018 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</Value></Opportunity><Opportunity><Value>Potential | This watershed has been degraded due to a large amount of dispersed camping, and unauthorized roads. This watershed is just upstream of Poncha Spring and Salida and provides some municipal water for these entities. | <Known_Partners><Partner><Name>Fountain Valley Schools</Name><Type>Known</Type></Partner></Known_Partners> | 2018-04-26 | 2022-09-30 | 6 | 1000000 | 2022-09-30 | Y | 0212 | Grays Creek-Poncha Creek Watershed Restoration Action Plan | 2018-04-26 |  | 11795.663 | 0.0065558 | 0.50661
Dixie National Forest | 140700050102 | Birch Creek | Functioning at Risk | 29277.6 | 86 | 14 | Good | Fair | Fair | Good | Fair | Poor | Fair | Fair | Fair | Good | Good | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</V | • Sediment contribution from the watershed: This watershed drains directly into the Escalante River which and is one of the major stream sources for filling the Wide Hollow Reservoir which is 303d listed for exceeding cold water temperatures and pH impa | <Known_Partners><Partner><Name>Utah State Division of Wildlife Resource</Name><Type>Known</Type></Partner><Partner><Name>Utah State Division of Forestry, Fire an</Name><Type>Known</Type></Partner><Partner><Name>Garfield County</Name><Type>Known</Type></Pa | 2011-09-30 | 2018-09-30 | 6 | 1700000 | 2013-09-30 | Y | 0407 | Birch Creek Watershed Action Plan | 2011-09-30 | Y | 25130.959 | 0.01212 | 0.6679
Uinta-Wasatch-Cache National Forest | 160102030207 | Left Hand Fork Blacksmith Fork Canyon | Functioning at Risk | 35661.7 | 92 | 8 | Fair | Fair | Good | Fair | Fair | Poor | Fair | Poor | Good | Good | Fair | Good | 2014 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Cost>&lt; $100,000</Cost></Principal_Reason> | Important area for water quality and aquatic habitat protection and improvement. High recreational use area with many access roads. Grazing also a use in the watershed. | <Known_Partners><Partner><Name>Trout Unlimited</Name><Type>Known</Type></Partner><Partner><Name>UT Partners for Consrvation and Developm</Name><Type>Known</Type></Partner><Partner><Name>UT Division of Wildlife Resources</Name><Type>Known</Type></Partner>< | 2014-05-05 | 2015-09-30 | 2 | 80000 | 2015-09-01 | Y | 0419 | Left Hand Fork Blacksmiths Fork | 2014-05-05 | Y | 32699.528 | 0.015608 | 0.85888
Lolo National Forest | 170102130403 | West Fork Fishtrap Creek | Functioning at Risk | 11588.3 | 99 | 1 | Good | Fair | Poor | Good | Fair | Poor | Good | Fair | Good | Good | Fair | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</ | The West Fork of Fishtrap Creek supports the bulk of fluvial bull trout spawning in the Fishtrap Creek watershed. This is a bull trout priority watershed and one of the two most important bull trout areas in the larger Thompson River system. Improvemen |  | 2011-10-28 | 2015-10-01 | 4 | 225000 | 2015-08-31 | Y | 0116 | West Fork Fishtrap Creek WRAP | 2011-10-28 | Y | 11486.671 | 0.005629 | 0.38223
Flathead National Forest | 170102110202 | Cold Creek | Functioning at Risk | 21490 | 96 | 4 | Fair | Poor | Good | Good | Good | Poor | Good | Good | Good | Good | Fair | ---- | 2013 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Invasive Species</Value></Concern></Concerns><Cost>&lt; $100,000</Cost></Principal_Reason> | Cold Creek is priority because it is in Class 2 condition and in need of some resource improvements. It is also a high priority in the R1 Bull Trout Conservation Strategy. | <Known_Partners><Partner><Name>Montana DEQ</Name><Type>Known</Type></Partner><Partner><Name>SEC</Name><Type>Known</Type></Partner></Known_Partners> | 2014-05-25 | 2017-09-30 | 4 | 120000 | 2017-09-30 | Y | 0110 | DRAFT Cold Creek Watershed Action Plan | 2014-05-25 | Y | 20651.8 | 0.010389 | 0.51903
Flathead National Forest | 170102110204 | Jim Creek | Functioning Properly | 11994.8 | 93 | 7 | Fair | Fair | Good | Good | Good | Good | Good | Good | Good | Good | Poor | ---- | 2013 | <Principal_Reason><Concerns><Concern><Value>Invasive Species</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Cost>&lt; $100,000</Cost></Principal_Reason> | Jim Creek is on the State 303(d) list for siltation. Jim Creek is also a high priority watershed in the R1 Bull Trout Conservation Strategy. | <Known_Partners><Partner><Name>Montana Fish, Wildlife and Parks</Name><Type>Known</Type></Partner><Partner><Name>Montana Dept of Environmental Quality</Name><Type>Known</Type></Partner></Known_Partners> | 2013-06-14 | 2017-08-05 | 3 | 120000 | 2017-09-30 | Y | 0110 | Jim Creek Watershed Action Plan | 2013-06-14 | Y | 11159.283 | 0.0058056 | 0.39795
Flathead National Forest | 170102100303 | Sheppard Creek | Functioning Properly | 24136.6 | 95 | 6 | Poor | Good | Good | Good | Good | Good | Good | Good | Good | Good | Fair | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Invasive Species</Value></Concern></Concerns><Cost>&lt; $100,000</Cost></Principal_Reason> | The vast majority of the Sheppard Creek watershed burned in 2007. Through Burned Area Emergency Response (BAER), several culverts were upgraded and weeds were treated along roads and trails. Post-fire timber salvage work was completed in the fall of 201 |  | 2012-08-21 | 2014-09-30 | 4 | 34500 | 2013-09-30 | Y | 0110 | Sheppard Creek Watershed Action Plan | 2012-08-21 | Y | 22803.427 | 0.011857 | 0.63146
Deschutes National Forest | 170703010904 | Lower Lake Creek | Functioning at Risk | 7124.2 | 79 | 21 | Fair | Good | Fair | Fair | Fair | Fair | Fair | Good | Good | Fair | Good | ---- | 2011 | <Principal_Reason><Resources><Resource><Value>Species Protection Area</Value></Resource></Resources><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</ | Many projects and partners are actively working for restoration of fish passage/fish screens, flow protection, riparian protection and floodplain protection. Chinook salmon and sockeye salmon are being reintroduced into the watershed in the next few year | <Known_Partners><Partner><Name>Upper Deschutes Watershed Council</Name><Type>Known</Type></Partner><Partner><Name>Friends of the Metolius</Name><Type>Known</Type></Partner><Partner><Name>Confederated Tribes of Warm Springs</Name><Type>Known</Type></Partne | 2011-09-26 | 2017-09-26 | 6 | 817500 | 2017-09-29 | Y | 0601 | Lower Lake Creek | 2011-09-26 | Y | 5649.613 | 0.003258 | 0.36707
Boise National Forest | 170501210102 | Bull Creek | Functioning Properly | 24282.1 | 100 | 0 | Poor | Fair | Good | Good | Good | Good | Good | Good | Good | Good | Fair | Good | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns><Opportunities><Opportunity><Value>Improve Condition</V | The Bull Creek subwatershed was identified in Watershed Condition Framework as impaired for the “Water Quality (not listed)” indicator due to known sediment delivery impacts related to deteriorating trail conditions. | <Known_Partners><Partner><Name>Idaho Dept. of Parks and Recreation</Name><Type>Known</Type></Partner><Partner><Name>Emmett Rough Riders ATV Club</Name><Type>Known</Type></Partner><Partner><Name>Squaw Butte Backcountry Horsemen</Name><Type>Known</Type></Pa |  |  |  | 379000 | 2012-09-30 |  | 0402 | No WRAP was developed for the Bull Creek subwatershed |  | Y | 24282.081 | 0.01111 | 0.63003
Plumas National Forest | 180201230401 | Big Grizzly Creek | Functioning at Risk | 33441.3 | 88 | 12 | Fair | Fair | Fair | Fair | Fair | Fair | Fair | Fair | Fair | Fair | Fair | Fair | 2011 | <Principal_Reason><Resources><Resource><Value>Other</Value></Resource><Resource><Value>Wild and Scenic River</Value></Resource><Resource><Value>Municipal Watershed</Value></Resource></Resources><Opportunities><Opportunity><Value>Improve Condition</Value>< | This watershed drains to the Middle Fork Feather River, a federally designated Wild and Scenic River. Most of the watershed drains to Lake Davis, an identified municipal water source. Lake Davis is also a very popular local recreation area and a trophy | <Known_Partners><Partner><Name>CA Dept of Water Resources</Name><Type>Known</Type></Partner><Partner><Name>Federal Highway Administration</Name><Type>Known</Type></Partner><Partner><Name>Quincy Library Group</Name><Type>Known</Type></Partner><Partner><Nam | 2011-10-24 | 2015-09-30 | 8 | 1840000 | 2017-07-30 | Y | 0511 | Big Grizzly Creek watershed restoration action plan | 2011-10-24 |  | 29320.823 | 0.014251 | 0.72219
Tongass National Forest | 190102110502 | Sitkoh Creek | Functioning Properly | 12127.9 | 100 | 0 | Good | Fair | Good | Good | Poor | Fair | Good | Good | Good | Good | Good | ---- | 2011 | <Principal_Reason><Concerns><Concern><Value>Riparian Structure and Function</Value></Concern><Concern><Value>Species Habitat</Value></Concern><Concern><Value>Water Quality</Value></Concern></Concerns></Principal_Reason> | There is concern for the long term health and function of aquatic and riparian habitat in the Sitkoh Creek watershed. A significant percentage of riparian area associated with large wood-dependent channels has been harvested or roaded. Indicators for In | <Known_Partners><Partner><Name>Sitka Conservation Society</Name><Type>Known</Type></Partner></Known_Partners> | 2011-01-01 | 2015-09-30 | 3 |  | 2015-09-30 | Y | 1005 | Sitkoh Creek | 2011-01-01 | Y | 12099.521 | 0.0073479 | 0.48975